## Slide 1
Decision needed: hold the 72-hour endurance run until the coupling retest passes
The pump drive end reads 6.8 mm/s RMS at 3,550 rpm against a 4.5 mm/s RMS limit, and the fix is not yet proven.
Sam Ortega, Systems Engineering. Source: Kestrel pump skid vibration test memo, 2026-10-08.

## Slide 2
Pump vibration exceeds the limit only at the top test speed
• Pump drive end: 6.8 mm/s RMS at 3,550 rpm.
• Program limit is 4.5 mm/s RMS at any bearing housing.
• Motor drive end is also over, at 4.6 mm/s RMS.
• All bearings are under the limit at 1,800 to 3,000 rpm.
• Both non-drive-end readings stay under the limit at 3,550 rpm.
Source: Kestrel pump skid vibration test memo, 2026-10-08, Results table.
Tarrant Dynamics | Internal
2

## Slide 3
The spectrum points to alignment or the coupling, not hydraulics
• 2x running speed peak: 5.9 mm/s RMS at 118.3 Hz.
• 1x peak is 2.1 mm/s RMS, which argues against imbalance.
• Vane pass peak is 0.8 mm/s RMS, which argues against hydraulics.
• A high 2x peak suggests misalignment or a coupling not absorbing it.
• Operating point was 176 m3/h at 41.2 m head.
Source: Kestrel pump skid vibration test memo, 2026-10-08, Spectrum at 3,550 rpm table.
Tarrant Dynamics | Internal
3

## Slide 4
Cold alignment was in tolerance, so the root cause is still open
• Parallel offset was 0.04 mm against a 0.10 mm tolerance.
• Angular offset was 0.03 mm/100 mm against a 0.05 mm/100 mm tolerance.
• Pump drive end climbed 3.9 to 6.8 mm/s RMS above 3,000 rpm.
• Suspects: motor frame thermal growth or VC-38 disc pack wear.
• Flag: no hot alignment reading was taken.
Source: Kestrel pump skid vibration test memo, 2026-10-08, Method and Spectrum sections.
Tarrant Dynamics | Internal
4

## Slide 5
Retest with the new coupling before the 72-hour run starts
• Install the replacement VC-38 coupling, expected 2026-10-12.
• Repeat the four-speed test from 1,800 to 3,550 rpm.
• Take a hot alignment reading right after the 3,550 rpm hold.
• Flag: the memo predicts the new coupling fixes it, untested.
• Start the 72-hour run only if both drive ends pass.
Source: Kestrel pump skid vibration test memo, 2026-10-08, Next steps.
Tarrant Dynamics | Internal
5